## List of Feature
No | List of Feature | Menu | Owner | Status | Persentase | Start date | End date | Notes | Monitoring Progress | Percentage
1 | Login/logout | Homescreen | Frontend Dev | In Progress | 20% | 2024-09-30 | 2024-10-04 | - FE Slicing Done - BE in progress di local | Homescreen | 20%
2 | Service login logout | Homescreen | Backend Dev | In Progress | 20% | 2024-09-30 | 2024-10-04 | - FE Slicing Done - BE in progress di local | Stok Bahan Baku Utama | 15%
3 | Home | Homescreen | Frontend Dev | In Progress | 20% | 2024-09-30 | 2024-10-04 | - FE Slicing Done - BE in progress di local | Dokumentasi Penerimaan Barang | 18.46%
4 | Menampilkan Stock Bahan Baku Utama | Stock Bahan Baku Utama | Frontend Dev | In Progress | 20% | 2024-09-30 | 2024-10-04 | - FE Slicing Done - BE in progress di local | Stok Opname | 0%
5 | API get stock bahan baku utama | Stock Bahan Baku Utama | Backend Dev | Open | 10% | 2024-09-30 | 2024-10-04 | - menunggu hasil normalisasi dan akun credential untuk akses google sheet | Overall Progress | 11.15%
6 | Menu Dokumentasi Penerimaan Barang | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local
7 | Cari nomor PO untuk input dokumentasi | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local
8 | API get data detail material by PO Number from SAP | Dokumentasi Penerimaan Barang | Backend Dev | Open | 10% | 2024-09-30 | 2024-10-04 | - menunggu konfirmasi url synchro - menunggu akses vpn dan server
9 | Menampilkan detail item PO | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local
10 | Ambil dan pilih gambar dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local
11 | Submit dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local
12 | API simpan data dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Backend Dev | In Progress | 20% | 2024-09-30 | 2024-10-04 | - FE Slicing Done - BE in progress di local
13 | Cari nomor PO untuk view dokumentasi | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local
14 | API get data dokumentasi penerimaan barang by PO Number | Dokumentasi Penerimaan Barang | Backend Dev | In Progress | 20% | 2024-09-30 | 2024-10-04 | - FE Slicing Done - BE in progress di local
15 | Menampilkan detail dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local |  | Status | Persentase
16 | Melihat dan menampilkan foto dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local |  | Pending | 0%
17 | Melakukan edit foto dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Frontend Dev | In Progress | 20% | 2024-10-07 | 2024-10-11 | - FE Slicing Done - BE in progress di local |  | Not Started | 0%
18 | API edit foto item OP dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Backend Dev | Open | 10% | 2024-09-30 | 2024-10-04 | - menunggu konfirmasi server storage - menunggu akses vpn dan server |  | Open | 10%
19 | API tambah foto item OP dokumentasi penerimaan barang | Dokumentasi Penerimaan Barang | Backend Dev | Open | 10% | 2024-09-30 | 2024-10-04 | - menunggu konfirmasi server storage - menunggu akses vpn dan server |  | In Progress | 20%
20 | Menu Stock Opname | Stock Opname | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Integrasi | 30%
21 | Melakukan scan barcode untuk stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | In Review | 40%
22 | Menampilkan warning saat material tidak ditemukan | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Modify Code | 50%
23 | Menampilkan detail material stock opname from SAP | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Resolved | 60%
24 | API get detail material from SAP | Stock Opname (submenu Scan Barcode) | Backend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Ready to Test | 70%
25 | Memasukan stock fisik pada form stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Feedback | 80%
26 | Memasukan catatan pada form stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Ready to be Released | 90%
27 | Melakukan draft stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18 |  |  | Completed | 100%
28 | Melakukan submit stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
29 | API simpan draft stock opname | Stock Opname (submenu Scan Barcode) | Backend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
30 | API simpan submit stock opname | Stock Opname (submenu Scan Barcode) | Backend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
31 | Menampilkan daftar review stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
32 | API get stock opname status is_submitted=false | Stock Opname (submenu Scan Barcode) | Backend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
33 | Menampilkan detail review stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
34 | API get detail stock opname | Stock Opname (submenu Scan Barcode) | Backend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
35 | Melakukan update stock fisik stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
36 | Melakukan update catatan stock opname | Stock Opname (submenu Scan Barcode) | Frontend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
37 | API update submit stock opname | Stock Opname (submenu Scan Barcode) | Backend Dev | Not Started | 0% | 2024-10-14 | 2024-10-18
38 | Melakukan scan barcode untuk cek stock | Stock Opname (submenu Cek Stock) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
39 | Menampilkan warning saat material tidak ditemukan | Stock Opname (submenu Cek Stock) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
40 | API get detail material from SAP | Stock Opname (submenu Cek Stock) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
41 | Tampilan awal submenu Report Stock Opname | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
42 | Pilih periode start date | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
43 | Pilih periode end date | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
44 | Membuat permohonan berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
45 | Mengirim notifikasi email ke pejabat (manager) bahwa ada permohonan berita acara stock opname yang harus dilakukan approval | Stock Opname (submenu Report Stock Opname) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
46 | API create berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
47 | Menampilkan daftar berita acara stock opname yang telah disetujui | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
48 | API get daftar berita acara stock opname yang telah disetujui | Stock Opname (submenu Report Stock Opname) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
49 | Melihat detail berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
50 | API get detail berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
51 | Download excel berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
52 | Download pdf berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
53 | API download excel berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
54 | API download pdf berita acara stock opname | Stock Opname (submenu Report Stock Opname) | Backend Dev | Not Started | 0% | 2024-10-21 | 2024-10-25
55 | Tampilan awal submenu Approval Stock Opname (My Request) | Stock Opname (submenu Approval My Request) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
56 | Menampilkan daftar permohonan berita acara stock opname | Stock Opname (submenu Approval My Request) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
57 | API get daftar berita acara stock opname by user yang login | Stock Opname (submenu Approval My Request) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
58 | Menampilkan detail permohonan berita acara stock opname | Stock Opname (submenu Approval My Request) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
59 | Menampilkan approval info permohonan berita acara stock opname | Stock Opname (submenu Approval My Request) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
60 | API get detail berita acara stock opname | Stock Opname (submenu Approval My Request) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
61 | Download excel berita acara stock opname | Stock Opname (submenu Approval My Request) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
62 | Download pdf berita acara stock opname | Stock Opname (submenu Approval My Request) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
63 | API download excel berita acara stock opname | Stock Opname (submenu Approval My Request) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
64 | API download pdf berita acara stock opname | Stock Opname (submenu Approval My Request) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
65 | Tampilan awal submenu Approval Stock Opname (Bucket Approval) | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
66 | Menampilkan daftar permohonan berita acara stock opname yang akan di approve | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
67 | API get daftar permohonan berita acara stock opname yang belum di approve siapapun | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
68 | API get daftar permohonan berita acara stock opname yang sudah di approve manager | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
69 | Menampilkan detail permohonan berita acara stock opname | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
70 | API get detail berita acara stock opname | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
71 | Download excel berita acara stock opname | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
72 | API download excel berita acara stock opname | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
73 | Memasukan catatan approval by manager | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
74 | Melakukan tolak permohonan by manager | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
75 | Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname ditolak manager, dan harus membuat permohonan ulang | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
76 | API update berita acara stock opname di tolak manager | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
77 | Melakukan setuju permohonan by manager | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
78 | Mengirim notifikasi email ke pejabat (senior manager) bahwa ada permohonan berita acara stock opname yang harus dilakukan approval | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
79 | Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname disetujui manager | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
80 | API update berita acara stock opname di setujui manager | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
81 | Memasukan catatan approval by senior manager | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
82 | Melakukan tolak permohonan by senior manager | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
83 | Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname ditolak senior manager, dan harus membuat permohonan ulang | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
84 | API update berita acara stock opname di tolak senior manager | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
85 | Melakukan setuju permohonan by senior manager | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
86 | Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname disetujui senior manager dan sudah bisa di download | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
87 | API update berita acara stock opname di setujui senior manager | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
88 | Download pdf berita acara stock opname | Stock Opname (submenu Approval Bucket Approval) | Frontend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31
89 | API download pdf berita acara stock opname | Stock Opname (submenu Approval Bucket Approval) | Backend Dev | Not Started | 0% | 2024-10-28 | 2024-10-31

## List Table
Tabel | users
ID | Coloumn Name | Data Type | Description | Note
Tabel | master_role
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data master role
2 | role_name | String | nama role
3 | role_desc | String | deskripsi role
4 | created_at | date | waktu create
5 | updated_at | date | waktu update
6 | created_by | String | nama user create
7 | updated_by | String | nama user update
Tabel | user_role
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data master role
2 | user_id | String | id user
3 | role_id | String | id role
4 | created_at | date | waktu create
5 | updated_at | date | waktu update
6 | created_by | String | nama user create
7 | updated_by | String | nama user update
Tabel | master_activity
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data master activity
2 | activity_id | String | id activity
3 | activity_name | String | nama activity
4 | activity_desc | String | deskripsi activity
Tabel | activity_log
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data activity log
2 | activity_id | String | FK id activity | looking ke tabel master_activity
3 | created_at | date | waktu activity
4 | created_by | String | user yang melakukan activity
Tabel | master_plant
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data activity log
2 | kode_plant | String | FK id activity | looking ke tabel master_activity
3 | nama_plant | date | waktu activity
4 | created_at | date | waktu create
5 | updated_at | date | waktu update
6 | created_by | String | nama user create
7 | updated_by | String | nama user update
Tabel | doc_good_receipts
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data dokumentasi penerimaan barang
2 | op_number | String | nomor Order Pembelian
3 | vendor_name | String | nama vendor
4 | dokumentasi_op_path | String | path hasil foto dokumentasi op
5 | tanggal_dokumentasi | date | tanggal dokumentasi
6 | created_at | date | waktu create
7 | updated_at | date | waktu update
8 | created_by | String | nama user create
9 | updated_by | String | nama user update
Tabel | detail_doc_good_receipt
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data detail dokumentasi penerimaan barang
2 | doc_good_receipt_id | uuid | FK doc_good_receipts
3 | kode_material | String | kode material
4 | desc_material | String | deskripsi material (short text)
5 | created_at | date | waktu create
6 | updated_at | date | waktu update
7 | created_by | String | nama user create
8 | updated_by | String | nama user update
Tabel | detail_item_op_doc_good_receipt
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data detail item op dokumentasi penerimaan barang
2 | detail_doc_good_receipt_id | uuid | FK detail_doc_good_receipt
3 | item_op_path | String | path foto dokumentasi item/material op
4 | created_at | date | waktu create
5 | updated_at | date | waktu update
6 | created_by | String | nama user create
7 | updated_by | String | nama user update
Tabel | stock_opname
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data stock opname
2 | plant_id
3 | kode_material | String | kode material
4 | desc_material | String | deskripsi material (short text)
5 | storage_bin | String | lokasi penyimpanan
6 | stock_sistem | Number | stok sistem dari SAP
7 | stock_fisik | Number | stok fisik di gudang
8 | stock_status | String | status stok (Sama atau Selisih)
9 | catatan | String | catatan stock opname | maksimal 250 karakter
10 | stock_opname_date | date | tanggal stock opname di submit | saat draft, stock opname date kosong
11 | is_submitted | boolean | flag untuk submitted, Draft = 0, Submit = 1
12 | created_at | date | waktu create
13 | updated_at | date | waktu update
14 | created_by | String | nama user create
15 | updated_by | String | nama user update
Tabel | report_stock_opname
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data report/berita acara stock opname
2 | kode_plant | String | kode plant
3 | periode_start_date | String | start date periode berita acara stock opname | looking ke stock_opname_date di table stock_opname
4 | periode_end_date | String | end date periode berita acara stock opname | looking ke stock_opname_date di table stock_opname
5 | berita_acara_number | String | nomor berita acara | format penomoran <nomor_BA>/BA-<kode_plant>/<bulan>.<tahun> ket : nomor_BA : nomor berita acara dengan format 5 digit dan auto increment by sistem, auto reset per tahun kode_plant : kode plant bulan : berupa 2 digit angka, contoh bulan januari, maka 01 tahun : berupa 4 digit tahun contoh berita_acara_number : 00012/BA-3781/10/2024
6 | stock_fisik | Number | stok fisik di gudang
7 | stock_status | String | status stok (Sama atau Selisih)
8 | catatan | String | catatan stock opname | maksimal 250 karakter
9 | stock_opname_date | date | tanggal stock opname | menyimpan tanggal saat stock opname sudah submit
10 | is_submitted | String | flag untuk submit stock opname | Submit = Y, Draft = N
11 | created_at | date | waktu create
12 | updated_at | date | waktu update
13 | created_by | String | nama user create
14 | updated_by | String | nama user update
Tabel | approval_ba_stock_opname
ID | Coloumn Name | Data Type | Description | Note
1 | uuid |  | id indexing untuk data approval berita acara stock opname
2 | report_stock_opname_id | uuid | FK report_stock_opname
3 | is_approved_by_manager | String | flag untuk approval manager | Setuju = Y, Tolak = N
4 | is_approved_by_senior_manager | String | flag untuk approval senior manager | Setuju = Y, Tolak = N
5 | note_approval_by_manager | String | catatan untuk approval manager
6 | note_approval_by_senior_manager | String | catatan untuk approval senior manager
7 | approval_by_manager_at | String | waktu untuk approval manager
8 | approval_by_senior_manager_at | String | waktu untuk approval senior manager
9 | approval_by_manager_by | String | nama manager yang approval
10 | approval_by_senior_manager_by | String | nama senior manager yang approval

## Master Activity
activity_id | activity_name | activity_desc
1 | Melihat Stock Bahan Baku Utama | saat buka menu Stock Bahan Baku Utama
2 | Membuat Dokumentasi Penerimaan Barang | klik submit saat input data Dokumentasi Penerimaan Barang
3 | Melihat Dokumentasi Penerimaan Barang | klik cari saat view data Dokumentasi Penerimaan Barang
4 | Mengedit Foto Item OP Dokumentasi Penerimaan Barang | klik update saat edit foto item OP Dokumentasi Penerimaan Barang
5 | Menambah Foto Item OP Dokumentasi Penerimaan Barang | klik simpan saat tambah foto item OP Dokumentasi Penerimaan Barang
6 | Membuat Draft Stock Opname | klik draft saat stock opname
7 | Melakukan Submit Stock Opname | klik submit saat stock opname
8 | Melihat Review Stock Opname | klik review stock opname
9 | Melakukan Submit Review Stock Opname | klik submit to update stock opname
10 | Melihat Stock Material | scan barcode untuk cek stock
11 | Membuat permohonan berita acara stock opname | klik permohonan berita acara
12 | Melihat daftar permohonan berita acara stock opname | klik submenu my request
13 | Melihat detail permohonan berita acara stock opname | klik lihat detail my request
14 | Download excel berita acara stock opname | klik download excel ba stock opname
15 | Download pdf berita acara stock opname | klik download pdf ba stock opname
16 | Melihat daftar approval berita acara stock opname | klik submenu bucket approval
17 | Manager menyetujui permohonan berita acara stock opname | saat manager klik tolak
18 | Manager menolak permohonan berita acara stock opname | saat manager klik setuju
19 | Senior Manager menyetujui permohonan berita acara stock opname | saat senior manager klik tolak
20 | Senior Manager menolak permohonan berita acara stock opname | saat senior manager klik setuju

## Master Plant
kode_plant | nama_plant
3701 | padang
4701 | tonasa
5701 | SG (Rembang)
7701 | SI (Gresik)
7702 | SI (Tuban)

## Role Matrix
Role | IT | User Gudang | User Non Gudang
Admin | ✓
Gudang, terdiri dari Menu: 1. Dashboard Stok Bahan Baku 2. Dokumentasi Penerimaan Barang 3. Stok Opname |  | ✓
Non Gudang, terdiri dari Menu: 1. Dashboard Stok Bahan Baku |  |  | ✓

## FE - Slicing
ID | List of Pages | Menu | Submenu | PIC | Status | Start date | End date | Notes | Persentase
FE-001 | Login |  |  | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 |  | 100% | Total
FE-002 | Halaman Utama/Home |  |  | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 |  | 100% | 100%
FE-003 | Menu Stock Bahan Baku Utama | STOCK BAHAN BAKU UTAMA |  | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 |  | 100%
FE-004 | Menu Dokumentasi Penerimaan Barang | DOKUMENTASI PENERIMAAN BARANG | Input Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 | form view data perlu di rename (done) | 100%
FE-005 | Input Data Dokumentasi Penerimaan Barang | DOKUMENTASI PENERIMAAN BARANG | Input Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 | tabel item OP di update jadi bentuk card (done) | 100%
FE-006 | Take dan Select Foto Saat Input Dokumentasi Penerimaan Barang | DOKUMENTASI PENERIMAAN BARANG | Input Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 | hanya bisa ambil gambar langsung dan bisa take lebih dari 1 foto (done) | 100%
FE-007 | Take Foto Dokumentasi OP | DOKUMENTASI PENERIMAAN BARANG | Input Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 |  | 100%
FE-008 | View Data Dokumentasi Penerimaan Barang | DOKUMENTASI PENERIMAAN BARANG | View & Edit Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 | update judul halaman dan button submit tidak perlu (done) | 100%
FE-009 | View Detail Lihat Foto Dokumentasi Penerimaan Barang | DOKUMENTASI PENERIMAAN BARANG | View & Edit Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 |  | 100%
FE-010 | Take dan Select Foto Saat Edit Dokumentasi Penerimaan Barang | DOKUMENTASI PENERIMAAN BARANG | View & Edit Data | Frontend Dev | Completed | 2024-09-26 | 2024-09-30 | hanya bisa ambil gambar langsung dan bisa take lebih dari 1 foto (done) | 100%
FE-011 | Menu Stock Opname | STOCK OPNAME |  | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-012 | Scan Barcode Stock Opname | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 | perlu menambahkan dropdown select plant | 100%
FE-013 | Form Input Stock Opname | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-014 | Daftar Review Stock Opname | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 | dibuat bentuk card | 100%
FE-015 | Form Update Stock Opname | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-016 | Scan Barcode Cek Stock | STOCK OPNAME | Stock Opname (submenu Cek Stock) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-017 | View Cek Stock | STOCK OPNAME | Stock Opname (submenu Cek Stock) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 | tidak perlu stock fisik dan catatan | 100%
FE-018 | Reporting Stock Opname | STOCK OPNAME | Stock Opname (submenu Report Stock Opname) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 | perlu menambahkan dropdown select plant | 100%
FE-019 | Approval BA Stock Opname (condition where manager / senior manager) | STOCK OPNAME | Stock Opname (submenu Approval) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-020 | My Request | STOCK OPNAME | Stock Opname (submenu Approval) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 | tabel my request di update jadi bentuk card (done) | 100%
FE-021 | Detail My Request | STOCK OPNAME | Stock Opname (submenu Approval) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-022 | Bucket Approval (condition where manager / senior manager) | STOCK OPNAME | Stock Opname (submenu Approval) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 | tabel my request di update jadi bentuk card (done) | 100%
FE-023 | Detail Approval BA Stock Opname (condition where manager) | STOCK OPNAME | Stock Opname (submenu Approval) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%
FE-024 | Detail Approval BA Stock Opname (condition where senior manager) | STOCK OPNAME | Stock Opname (submenu Approval) | Frontend Dev | Completed | 2024-10-01 | 2024-10-04 |  | 100%

## BE
ID | List of Service | Menu | Description | PIC | Status | Start date | End date | Notes | Persentase
BE-001 | login/logout | Login/Logout | Service login logout | Backend Dev | In Progress | 2024-09-30 | 2024-10-02 | per tgl 30 Sept belum dapat akses server dev dan vpn | 50% | Total
BE-002 | get_stock_bahan_baku_utama_by_spreadsheet | STOCK BAHAN BAKU UTAMA | API get stock bahan baku utama | Backend Dev |  |  |  | from google sheet perlu credential untuk akses google spreadsheet nya | 0% | 10%
BE-003 | get_dashboard_data | STOCK BAHAN BAKU UTAMA | API get data stock bahan baku utama untuk ditampilkan di dashboard | Backend Dev |  |  |  | perlu diskusi lanjutan terkait dashboard | 0%
BE-004 | get_list_material_by_op_number_from_sap | DOKUMENTASI PENERIMAAN BARANG | API get data detail material by nomor OP from SAP | Backend Dev | Open | 2024-09-30 | 2024-10-02 | per tgl 30 Sept belum dapat akses server dev dan vpn | 5%
BE-005 | create_doc_good_receipt | DOKUMENTASI PENERIMAAN BARANG | API simpan data dokumentasi penerimaan barang | Backend Dev | In Progress | 2024-09-30 | 2024-10-02 | - per tgl 30 Sept belum dapat akses server dev dan vpn - per tgl 1 okt on progress | 50%
BE-006 | get_doc_good_receipt_by_op_number | DOKUMENTASI PENERIMAAN BARANG | API get data dokumentasi penerimaan barang by nomor OP | Backend Dev | In Progress | 2024-09-30 | 2024-10-02 | - per tgl 30 Sept belum dapat akses server dev dan vpn - per tgl 1 okt on progress | 50%
BE-007 | get_detail_item_op_doc_good_receipt_by_id | DOKUMENTASI PENERIMAAN BARANG | API get foto dokumentasi penerimaan barang by id item op | Backend Dev | Open | 2024-09-30 | 2024-10-02 | per tgl 30 Sept belum dapat akses server dev dan vpn | 5%
BE-008 | create_detail_item_op_doc_good_receipt_by_id | DOKUMENTASI PENERIMAAN BARANG | API tambah foto dokumentasi penerimaan barang by id item op | Backend Dev | Open | 2024-09-30 | 2024-10-02 | per tgl 30 Sept belum dapat akses server dev dan vpn | 5%
BE-009 | update_detail_item_op_doc_good_receipt_by_id | DOKUMENTASI PENERIMAAN BARANG | API edit foto dokumentasi penerimaan barang by id item op | Backend Dev | Open | 2024-09-30 | 2024-10-02 | per tgl 30 Sept belum dapat akses server dev dan vpn | 5%
BE-010 | get_detail_material_scan_barcode_from_sap | Stock Opname (submenu Scan Barcode) | API get detail material from SAP | Backend Dev |  | 2024-10-03 | 2024-10-05 |  | 0%
BE-011 | create_stock_opname_draft | Stock Opname (submenu Scan Barcode) | API simpan draft stock opname | Backend Dev | In Progress | 2024-10-03 | 2024-10-05 |  | 50%
BE-012 | create_stock_opname_submit | Stock Opname (submenu Scan Barcode) | API simpan submit stock opname | Backend Dev | In Progress | 2024-10-03 | 2024-10-05 |  | 50%
BE-013 | get_list_stock_opname_drafted_by_user | Stock Opname (submenu Review Stock Opname) | API get daftar stock opname status is_submitted=false | Backend Dev |  | 2024-10-03 | 2024-10-05 |  | 0%
BE-014 | get_stock_opname_by_id | Stock Opname (submenu Review Stock Opname) | API get detail stock opname | Backend Dev |  | 2024-10-03 | 2024-10-05 |  | 0%
BE-015 | update_submit_stock_opname_by_id | Stock Opname (submenu Review Stock Opname) | API update submit stock opname | Backend Dev |  | 2024-10-03 | 2024-10-05 |  | 0%
BE-016 | get_detail_material_scan_barcode_from_sap | Stock Opname (submenu Cek Stock) | API get detail material from SAP | Backend Dev |  | 2024-10-03 | 2024-10-05 |  | 0%
BE-017 | create_ba_stock_opname | Stock Opname (submenu Report Stock Opname) | API create berita acara stock opname Mengirim notifikasi email ke pejabat (manager) bahwa ada permohonan berita acara stock opname yang harus dilakukan approval | Backend Dev |  | 2024-10-07 | 2024-10-09 |  | 0%
BE-018 | get_ba_stock_opname_by_id | Stock Opname (submenu Approval) | API get detail berita acara stock opname | Backend Dev |  | 2024-10-07 | 2024-10-09 |  | 0%
BE-019 | download_excel_ba_stock_opname | Stock Opname (submenu Approval) | API download excel berita acara stock opname | Backend Dev |  | 2024-10-07 | 2024-10-10 |  | 0%
BE-020 | download_pdf_ba_stock_opname | Stock Opname (submenu Approval) | API download pdf berita acara stock opname | Backend Dev |  | 2024-10-07 | 2024-10-10 | Masih menunggu template pdf dari SIG | 0%
BE-021 | get_list_ba_stock_opname_by_user | Stock Opname (submenu Approval) | API get daftar berita acara stock opname by user yang login | Backend Dev |  | 2024-10-07 | 2024-10-11 |  | 0%
BE-022 | get_list_ba_stock_opname_to_manager | Stock Opname (submenu Approval) | API get daftar permohonan berita acara stock opname yang belum di approve siapapun | Backend Dev |  | 2024-10-07 | 2024-10-11 |  | 0%
BE-023 | get_list_ba_stock_opname_to_senior_manager | Stock Opname (submenu Approval) | API get daftar permohonan berita acara stock opname yang sudah di approve manager | Backend Dev |  | 2024-10-07 | 2024-10-11 |  | 0%
BE-024 | update_approval_ba_stock_opname_by_id | Stock Opname (submenu Approval) | API update berita acara stock opname di tolak manager Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname ditolak manager, dan harus membuat permohonan ulang | Backend Dev |  | 2024-10-07 | 2024-10-15 |  | 0%
BE-025 | update_approval_ba_stock_opname_by_id | Stock Opname (submenu Approval) | API update berita acara stock opname di setujui manager Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname disetujui manager Mengirim notifikasi email ke pejabat (senior manager) bahwa ada permohonan berita acara stock opname yang harus dilakukan approval | Backend Dev |  | 2024-10-07 | 2024-10-15 |  | 0%
BE-026 | update_approval_ba_stock_opname_by_id | Stock Opname (submenu Approval) | API update berita acara stock opname di tolak senior manager Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname ditolak senior manager, dan harus membuat permohonan ulang | Backend Dev |  | 2024-10-07 | 2024-10-15 |  | 0%
BE-027 | update_approval_ba_stock_opname_by_id | Stock Opname (submenu Approval) | API update berita acara stock opname di setujui senior manager Mengirim notifikasi email ke requestor bahwa permohonan berita acara stock opname disetujui senior manager dan sudah bisa di download | Backend Dev |  | 2024-10-07 | 2024-10-15 |  | 0%
BE-028 | create_plant |  |  | Backend Dev | Completed |  |  |  | 100%
BE-029 | view_plant |  |  | Backend Dev | Completed |  |  |  | 100%
BE-030 | update_plant |  |  | Backend Dev | Completed |  |  |  | 100%
BE-031 | delete_plant |  |  | Backend Dev | Completed |  |  |  | 100%
BE-032 | create_m_activity |  |  | Backend Dev | Completed |  |  |  | 100%
BE-033 | view_m_activity |  |  | Backend Dev | Completed |  |  |  | 100%
BE-034 | update_m_activity |  |  | Backend Dev | Completed |  |  |  | 100%
BE-035 | delete_m_activity |  |  | Backend Dev | Completed |  |  |  | 100%

## FE BE - Integration
ID | Page Name | PIC | Status | Menu | Submenu | Requirement | Related Service | Data | Start date | End date | Notes
FE-001 | Login/logout | Frontend Dev | Open |  |  | Definition of Done : - login dengan SSO di SIG Data Display : - Condition / Validation : - jika username dan password tidak sesuai menampilkan pesan error | - login/logout | Input : - Output : - | 2024-10-07 | 2024-10-11
FE-002 | Halaman Utama/Home | Frontend Dev | Open |  |  | Desc : - menampilkan waktu saat ini (current time) - menampilkan nama user yang sedang login - menampilkan jabatan user yang sedang login - menampilkan menu sesuai role user yang sedang login | - |  | 2024-10-07 | 2024-10-11
FE-003 | Menu Stock Bahan Baku Utama (Perlu Diskusi Lanjutan untuk pembuatan dashboard) | Frontend Dev |  | STOCK BAHAN BAKU UTAMA |  | Desc : - menampilkan dashboard stock bahan baku utama Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-07 | 2024-10-11
FE-004 | Menu Dokumentasi Penerimaan Barang | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | Input Data | Desc : - menampilkan submenu Input Data - menampilkan submenu View Data - melakukan cari nomor OP di submenu Input Data - melakukan cari nomor OP di submenu View Data Data Display : - Condition / Validation : - submenu input data : jika nomor OP tidak ditemukan, maka menampilkan pesan error "Nomor OP tidak ditemukan" - submenu input data : jika nomor OP ditemukan, maka langsung menuju halaman Input Dokumentasi Penerimaan Barang - submenu view data : jika nomor OP tidak ditemukan, maka menampilkan pesan error "Data tidak ditemukan, belum pernah dilakukan pengambilan foto" - submenu view data : jika nomor OP ditemukan, maka langsung menuju halaman View Data Dokumentasi Penerimaan Barang | - hit API BE-004 get_list_material_by_op_number_from_sap (klik cari submenu input data) - hit API BE-006 get_doc_good_receipt_by_po_number (klik cari submenu view data) | Input : For API BE-004 get_list_material_by_op_number_from_sap - op_number For API BE-006 get_doc_good_receipt_by_po_number - op_number Output : From API BE-004 get_list_material_by_op_number_from_sap - op_number - vendor_name - list material (item OP, kode material dan desc material) From API BE-006 get_doc_good_receipt_by_po_number - doc_good_receipt_id - op_number - vendor_name - daftar item/material op (detail_doc_good_receipt_id, item OP, kode material dan desc material) | 2024-10-07 | 2024-10-11
FE-005 | Input Data Dokumentasi Penerimaan Barang | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | Input Data | Desc : - melakukan input data dokumentasi penerimaan barang - dapat melakukan cari item OP pada halaman input Data Display : - nomor OP - nama vendor - daftar item OP (kode material, desc material short text) Condition / Validation : - jika belum take foto Dokumentasi OP, maka tidak bisa submit - jika memaksa kembali/keluar dari menu ini, maka tampil pesan error "Peringatan: Data anda belum disubmit. Jika Anda meninggalkan halaman ini, perubahan akan hilang. Apakah Anda yakin ingin keluar?" - setelah submit menampilkan pop-up "Berhasil Submit Dokumentasi Penerimaan Barang" dan langsung menuju halaman utama menu Dokumentasi Penerimaan Barang | - hit API BE-005 create_doc_good_receipt saat klik tombol Submit | Input : For API BE-005 create_doc_good_receipt - op_number - vendor_name - dokumentasi_op_path - tanggal_dokumentasi - array material (kode_material, desc_material) - array path foto masing-masing item op (item_op_path) Output : - Berhasil Submit Dokumentasi Penerimaan Barang | 2024-10-07 | 2024-10-11
FE-006 | Take dan Select Foto Saat Input Dokumentasi Penerimaan Barang | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | Input Data | Desc : - take foto hanya bisa langsung by kamera, tidak bisa by galeri - hanya bisa input maksimal 3 gambar per item/material OP Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-07 | 2024-10-11
FE-007 | Take dan Select Foto Dokumentasi PO | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | Input Data | Desc : - take foto hanya bisa 1 foto - pastikan foto tidak buram - saat klik simpan menampilkan modal konfirmasi bahwa pastikan foto sudah jelas dan tidak buram Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-07 | 2024-10-11
FE-008 | View Data Dokumentasi Penerimaan Barang | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | View & Edit Data | Desc : - melihat hasil foto Dokumentasi OP - dapat melakukan cari item OP pada halaman view dokumentasi penerimaan barang - aksi lihat foto pada masing-masing item OP Data Display : get From Output API BE-006 get_doc_good_receipt_by_po_number - nomor OP - nama vendor - daftar item/material OP (detail_doc_good_receipt_id, kode material, desc material short text) Condition / Validation : - tombol Dokumentasi OP hanya view hasil foto saja, tidak bisa edit dan hapus - fitur cari item OP : jika data item OP tidak ditemukan, menampilkan data tidak ditemukan | - hit API BE-007 get_detail_item_op_doc_good_receipt_by_id saat klik aksi Lihat Foto | Input : For API BE-007 get_detail_item_op_doc_good_receipt_by_id - detail_doc_good_receipt_id Output : From API BE-007 get_detail_item_op_doc_good_receipt_by_id - array data foto item/material OP (id, item_op_path) | 2024-10-07 | 2024-10-11
FE-009 | View Detail Lihat Foto Dokumentasi Penerimaan Barang | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | View & Edit Data | Desc : - melihat list foto pada item/material OP yang di pilih - melakukan edit foto item/material OP Data Display : get From output API BE-007 get_detail_item_op_doc_good_receipt_by_id - daftar foto item/material OP Condition / Validation : - | - | Input : - Output : - | 2024-10-07 | 2024-10-11
FE-010 | Take dan Select Foto Saat Edit Dokumentasi Penerimaan Barang | Frontend Dev |  | DOKUMENTASI PENERIMAAN BARANG | View & Edit Data | Desc : - take foto hanya bisa 1 foto Data Display : - foto item op yang akan di edit Condition / Validation : - setelah update menampilkan pop-up "Berhasil Update Foto" dan kembali ke halaman View Detail Lihat Foto Dokumentasi Penerimaan Barang | - hit API BE-008 update_detail_item_op_doc_good_receipt_by_id saat update foto item/material OP | Input : - id dari detail_item_op_doc_good_receipt Output : - Berhasil Update Foto | 2024-10-07 | 2024-10-11
FE-011 | Menu Stock Opname | Frontend Dev |  | STOCK OPNAME |  | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-012 | Scan Barcode Stock Opname | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-013 | Form Input Stock Opname | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-014 | Daftar Review Stock Opname | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-015 | Form Update Stock Opname | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Scan Barcode) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-016 | Scan Barcode Cek Stock | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Cek Stock) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-017 | View Cek Stock | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Cek Stock) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : - | 2024-10-14 | 2024-10-18
FE-018 | Reporting Stock Opname | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Report Stock Opname) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-019 | Approval BA Stock Opname 1 | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-020 | My Request | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-021 | Detail My Request | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-022 | Approval BA Stock Opname 2 | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-023 | Bucket Approval (condition where manager) | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-024 | Bucket Approval (condition where senior manager) | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-025 | Detail Approval BA Stock Opname (condition where manager) | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -
FE-026 | Detail Approval BA Stock Opname (condition where senior manager) | Frontend Dev |  | STOCK OPNAME | Stock Opname (submenu Approval) | Desc : - Data Display : - Condition / Validation : - | - | Input : - Output : -